## Abstract
RA-2
+
Quantity executed since last bill | Quantity executed up to date as per measurement book | Total Executed Quantity | Item No. | Item of Work |  | Rate | Unit | Payment on the basis of actual measurement
123.14 | 0 | 123.14 | 1 | Excavation for foundation for depth from 1.5 mt to 3.0 mt including sorting out, stcking of useful material & disposing off material up to 50 mt lead. |  | 400 | Cu. Mt | 49256
7.26 | 3.8 | 11.06 | 2 | Providing & laying Cement Concrete 1:3:6 (1 Cement:3 coarse sand: 6 hand broken stone aggregates 40 mm(nominal size) and curing complete including cost of form work in (A)foundation &plinth |  | 4200 | Cu. Mt | 30492
5.36 | 0 | 5.36 | 3 | Providing & laying Controlled Cement concrete M-200 and curing complete including cost of formwork but excluding the cost of reinforcement for R.C.C. work (A) FOOTING |  | 11300 | Cu. Mt | 60568
7.72 | 3.4 | 11.12 | 4 | Providing & laying Controlled Cement concrete M-200 and curing complete including cost of formwork but excluding the cost of reinforcement for R.C.C. work (B) Columns having cross sectional area 0.05 to 0.08 sq.mt. |  | 13000 | Cu. Mt | 100360
37.79 | 3.43 | 41.22 | 5 | Providing & laying Controlled Cement concrete M-200 and curing complete including cost of formwork but excluding the cost of reinforcement for R.C.C. work (A) Beams having cross sectional area >0.08 &up to 0.12 sq.mt. |  | 13000 | Cu. Mt | 491270
223.23 | 0 | 223.23 | 6 | Filling in foundation & plinth with murrum or selected soil in layers of 20 cm thick including watering , ramming & consolidating etc. complete |  | 550 | Sq. Mt | 122776.5
139.52 | 0 | 139.52 | 7 | Filling in plinth with brick bat in layer of 20 cm thickness including watering ramming & consolidating etc. complete |  | 1100 | Sq. Mt | 153472
48.56 | 0 | 49.31 | 8 | Providing and laying controlled cement concrete M-200 and curing complete including the cost of formwork and reinforcement for R.C.C. work in (C)slabs, landing,shelves,balconies,lintels,beams, Girders and cantilever upto floor two level |  | 13000 | Kgs | 631280
5.77 | 59.08 | 64.85 | 9 | Brick work using common burnt clay building brick having crushing strength not less than 35 kg/sq.cm in foundation & plinth in cement mortar 1:5 ( 1 Cement : 5fine sand) (B) Conventional |  | 1700 | Cu. Mt | 9809
256.63 | 0 | 256.63 | 10 | Brick work using common burnt clay building brick having crushing strength not less than 35 kg/sq.cm in SUPERSTRUCTURE in cement mortar 1:5 ( 1 Cement: 5fine sand) (B) Conventional |  | 1700 | Cu. Mt | 436271
630.704 | 47.32 | 678.024 | 11 | 20 mm thick sand faced cement plaster on wall upto 10 meters above ground levelconsisting of 12 mm thick backing coat of c.m. 1:3 (1 cement:3 sand) and 8 mm thick finishing coat of c.m.1:1 ( 1cement: 1 white sand) etc. complete |  | 675 | Sq. Mt | 425725.2
219.3 | 0 | 219.3 | 12 | Providing and laying cement based water proofing of average 100mm thick in proper slope as per specifications:(a)cleaning rcc slab and and applying neat cement slurry mixed with water proofing compound.(b)providing and laying brickbat coba in CM1:4 mixed with water proofing compoundand curing for period of 24 hours (c ) laying of 25 mm thick PCC 1:1.5:3 mix with 6mm & down size coarse aggregate and water proofing compound,finishing smooth,making half round vata at the junction of parapet wall&slab,and curing for 10 days |  | 1300 | Cu. Mt | 285090
11102 | 1300 | 12402 | 13 | Providing TMT FE- 415 bar reinforcement for RCC work including bending & placing in position complete upto floor two level smooth. |  | 90 | Kgs | 999180
34 | 0 | 34 | 14 | Providing & anchoring 16 mm tor bars as anchor bars with chemicals of standard company by drilling holes 150 mm deep, cleaning the hole etc. |  | 2000 | Nos | 68000
|  |  |  | GRAND TOTAL |  |  |  | 3863549.7

## MB
Excavation for foundation for depth from 1.5 mt to 3.0 mt including sorting out, stcking of useful material & disposing off material up to 50 mt lead.
Sr. No. | Description |  | No. | L | B | D | Qty | Unit
1 | FOOTING |  | 1 | 14.8 | 3.2 | 2.6 | 123.136 | CMt
[5 empty] | GRAND TOTAL |  | 123.136 | Sq. Mt
[5 empty] | 123.136 | 400 | 49254.4 | IRS
Item No.2 Providing & laying Cement Concrete1:3:6 (1 Cement:3 coarse sand: 6 hand broken stone aggregates 40 mm(nominal size) and curing complete including cost of form work in (A)foundation &plinth
Sr. No. | Description |  | No. | L | B | D | Qty | Unit
1 | FOOTING AREA |  | 1 | 14.8 | 3 | 0.15 | 6.66 | CMt
2 | STAIR-CASE |  | 1 | 2.8 | 0.96 | 0.075 | 0.2016 | CMt
3 | STAIR-CASE |  | 2 | 2.8 | 0.96 | 0.075 | 0.4032 | CMt
[5 empty] | GRAND TOTAL |  | 7.2648 | Sq. Mt
[5 empty] | 7.2648 | 4200 | 30512.16 | IRS
Providing & laying Controlled Cement concrete M-200 and curing complete including cost of formwork but excluding the cost of reinforcement for R.C.C. work (A) FOOTINGS
Sr. No. | Description |  | No. | L | B | D | Qty | Unit
ECCENTRIC FOOTING
1 | F | 1 & 2 | 2 | 1.52 | 0.45 | 0.45 | 0.6156 | CMt
2 | F | 1 & 2 | 2 | 1.52 | 1.52 | 0.23 | 1.0628 | CMt
3 | F | 1 & 2 | 1 | 1.07 | 1.52 | 0.295 | 0.47979 | CMt
TRAPEZOIDAL FOOTING
4 | F | 3 & 4 |  |  |  |  | 0 | CMt
| A1= |  | 2 | 1.83 | 1.83 |  | 3.3489 | CMt
| A2= |  | 2 | 1.52 | 1.52 |  | 2.3104 | CMt
| H= |  |  | 0.525 | 0.23 |  | 0.295 | CMt
| H/3= | [5 empty] | 0.098333 | CMt
| A1+A2= | [5 empty] | 5.6593 | CMt
| √A1A2= | [5 empty] | 2.7816 | CMt
| [(A1+A2)+(√A1A2)}= | [5 empty] | 0.83002 | CMt
| BASE = | [5 empty] | 0.77025 | CMt
| TOTAL QTY. |  | 2 |  |  |  | 3.2005 | CMt
[5 empty] | GRAND TOTAL |  | 5.3587 | Sq. Mt
[5 empty] | 5.3587 | 11300 | 60553.4192 | IRS
Providing & laying Controlled Cement concrete M-200 and curing complete including cost of formwork but excluding the cost of reinforcement for R.C.C. work (B) Columns having cross sectional area 0.05 to 0.08 sq.mt. | [11 empty] | 0.45 | 0.45 | 0.2025
Sr. No. | Description |  | No. | L | B | D | Qty | Unit
1 | C | MAIN | 7 | 0.786 | 0.2025 | 4 | 4.4566 | CMt
2 | C | PARAPET | 4 | 0.45 | 0.45 | 1.2 | 0.972 | CMt
3 | C | PARAPET | 7 | 0.23 | 0.23 | 1 | 0.3703 | CMt
4 | C | FOOTING | 4 | 0.45 | 0.45 | 2.37 | 1.9197 | CMt
[5 empty] | GRAND TOTAL |  | 7.7186 | Sq. Mt
[5 empty] | 7.7186 | 13000 | 100342.06 | IRS
Providing & laying Controlled Cement concrete M-200 and curing complete including cost of formwork but excluding the cost of reinforcement for R.C.C. work (A) Beams having cross sectional area >0.08 &up to 0.12 sq.mt
Sr. No. | Description |  | No. | L | B | D | Qty | Unit
1 | B | 5 | 1 | 2.04 | 0.45 | 0.45 | 0.4131 | CMt
2 | B | 5 | 1 | 3.42 | 0.45 | 0.45 | 0.69255 | CMt
3 | B | 5 | 1 | 2.57 | 0.45 | 0.45 | 0.52042 | CMt
4 | B | 5 | 1 | 2.96 | 0.45 | 0.45 | 0.5994 | CMt |  | 3.21
5 | B | 5-R2 | 1 | 2.04 | 0.3 | 0.675 | 0.4131 | CMt |  | 3.21
6 | B | 5-R2 | 1 | 3.42 | 0.3 | 0.675 | 0.69255 | CMt |  | 0.375
7 | B | 5-R2 | 1 | 2.57 | 0.3 | 0.675 | 0.52043 | CMt
8 | B | 5-R2 | 1 | 2.96 | 0.3 | 0.675 | 0.5994 | CMt
9 | B | 5-R2 | 1 | 2.3 | 0.3 | 0.675 | 0.46575 | CMt
10 | B | 4-R2 | 1 | 6.8 | 0.3 | 0.675 | 1.377 | CMt
11 | B | 5-R2 | 1 | 2.85 | 0.3 | 0.675 | 0.57712 | CMt
12 | B | 5-R3 | 1 | 3.3 | 0.3 | 0.675 | 0.66825 | CMt
13 | B | 4-R3 | 1 | 6.86 | 0.3 | 0.675 | 1.3891 | CMt
14 | B | 5-R3 | 1 | 2.51 | 0.3 | 0.675 | 0.50827 | CMt
15 | B | 5-R3 | 1 | 2.51 | 0.3 | 0.675 | 0.50827 | CMt
16 | B | 4-R3 | 1 | 6.86 | 0.3 | 0.675 | 1.3891 | CMt
17 | B | 5-R3 | 1 | 3.3 | 0.3 | 0.675 | 0.66825 | CMt |  | 3.3
18 | B | 6 | 8 | 3.07 | 0.23 | 0.675 | 3.8129 | CMt
19 | CB | 1 | 2 | 1 | 0.23 | 0.675 | 0.3105 | CMt
20 | CB | 1 | 9 | 1.23 | 0.23 | 0.675 | 1.7186 | CMt
21 | B | 3 | 1 | 8.71 | 0.3 | 0.675 | 1.7638 | CMt
22 | B | 2 | 1 | 8.71 | 0.3 | 0.675 | 1.7638 | CMt
23 | B | 2 | 1 | 8.71 | 0.3 | 0.675 | 1.7638 | CMt
24 | B | 2 | 1 | 8.71 | 0.3 | 0.675 | 1.7638 | CMt
21 | B | 2 | 1 | 8.71 | 0.3 | 0.675 | 1.7638 | CMt
22 | B | 2 | 1 | 8.71 | 0.3 | 0.675 | 1.7638 | CMt
23 | B | 1 | 1 | 8.11 | 0.375 | 0.375 | 1.1405 | CMt
24 | B | 2 | 1 | 8.71 | 0.3 | 0.675 | 1.7638 | CMt
25 | B | 3 | 1 | 8.71 | 0.3 | 0.675 | 1.7638 | CMt
26 | 1 | EJ-H | 1 | 7 | 1.1 | 0.075 | 0.5775 | Sq. Mt
27 | 2 | EJ-V | 1 | 7 | 0.075 | 0.325 | 0.17063 | Sq. Mt
28 | 3 | EJ-H | 1 | 2.4 | 0.075 | 0.5 | 0.09 | Sq. Mt
29 | 4 | EJ-V | 1 | 2.4 | 0.26 | 0.075 | 0.0468 | Sq. Mt |  |  |  | 3.42
28 | 3-A | EJ-H | 1 | 3.6 | 0.36 | 0.5 | 0.648 | Sq. Mt
30 | 1 | EJ-V | 1 | 6 | 0.36 | 0.5 | 1.08 | Sq. Mt
32 | 3 | EJ-V | 1 | 4 | 0.36 | 0.5 | 0.72 | Sq. Mt
33 | 4 | EJ-V | 1 | 2.8 | 1.08 | 0.45 | 1.3608 | Sq. Mt |  |  |  | 3.42
[5 empty] | GRAND TOTAL |  | 37.7886 | Sq. Mt
[5 empty] | 37.7886 | 13000 | 491252.1412 | IRS
Filling in foundation & plinth with murrumor selected soil in layers of 20 cm thick including watering , ramming & consolidating etc. complete
Sr. No. | Description |  | No. | L | B | D | Qty | Unit
1 | Plinth Slab |  | 1 | 27.25 | 5.12 | 1.6 | 223.232 | CMt
[5 empty] | GRAND TOTAL |  | 223.232 | Sq. Mt
| Description |  |  |  | 223.232 | 550 | 122777.6 | IRS
Filling in plinth with brick bat in layer of 20 cm thick inculding watering, ramming & consolidating etc. complete.
Sr. No. | Description |  | No. | L | B | D | Qty | Unit |  | 1 | 27.25 | 5.12 | 0.1 | 13.952 | 13000 | 181376
1 | Plinth Slab |  | 1 | 27.25 | 5.12 | 1 | 139.52 | CMt
[5 empty] | GRAND TOTAL |  | 139.52 | Sq. Mt
| Description |  |  |  | 139.52 | 1100 | 153472 | IRS
પ્લીન્થ સ્લેબ માં ચિરાગ જોડે વિચાર વિમર્શ કરી ને PCC જે ૧૫૦ એમ એમ કરવાનું હતું એની જગ્યા એ M -૨૦ ૧૦૦ એમ એમ કરેલ હતું. | [9 empty] | 1 | 27.25 | 5.12 | 0.1 | 13.952 | 13000 | 181376
Providing and laying controlled cement concrete M-200 and curing complete including the cost of formwork and reinforcement for R.C.C. work in (C)slabs,landing,shelves,balconies,lintels,beams,Girders and cantilever upto floor two level
Sr. No. | Description |  | No. | L | B | D | Qty | Unit |  | 1 | 27.25 | 5.12 | 0.1 | 13.952 | 13000 | 181376
1 | Plinth Slab |  | 1 | 25.8 | 5.12 | 0.1 | 13.2096 | CMt
1 | Main Slab |  | 1 | 27.8 | 10.39 | 0.125 | 36.1053 | CMt
DEDUCTION |  |  | 1 | 2.52 | 2.4 | 0.125 | 0.756 | CMt
TOTAL AFTER DUDUCTION | [6 empty] | 48.5589
[5 empty] | GRAND TOTAL |  | 48.56 | Sq. Mt
[5 empty] | 48.56 | 13000 | 631280 | IRS
Item No.7 Brick work using common burnt clay building brick having crushing strengthnot less than 35 kg/sq.cm in foundation & plinth in cement mortar 1:5 ( 1 Cement: 5fine sand) (B) Conventional
1 | PB | 1st | 1 | 5.25 | 0.5 |  | 2.625 | CMt
2 | PB | LAST | 1 | 4.5 | 0.7 |  | 3.15 | CMt | 5.15
[5 empty] | GRAND TOTAL |  | 5.775 | Sq. Mt | 1.18 | 6.33 |  | 0.45
[5 empty] | 5.77 | 1700 | 9809 | IRS |  |  |  | 3
Item No.7 Brick work using common burnt clay building brick having crushing strengthnot less than 35 kg/sq.cm in SUPERSTRUCTURE in cement mortar 1:5 ( 1 Cement: 5fine sand) (B) Conventional
Sr. No. | Description |  | No. | L | B | D | Qty | Unit | 2.96
1 | 1 | EJ | 2 | 7 | 3.2 | 1 | 44.8 | Sq. Mt | 0.45
2 | 2 | EJ | 2 | 6 | 3.1 | 1 | 37.2 | Sq. Mt | 0.45
3 | 3 | EJ | 2 | 6 | 3.15 | 1 | 37.8 | Sq. Mt
4 | 4 | EJ | 2 | 6.8 | 3.15 | 1 | 42.84 | Sq. Mt |  |  |  | 3.42
5 | 1 | PW | 1 | 2.04 | 1.2 | 1 | 2.448 | Sq. Mt |  |  |  | 2.57
6 | 2 | PW | 1 | 3.42 | 1.2 | 1 | 4.104 | Sq. Mt |  |  |  | 0.45
7 | 3 | PW | 1 | 2.57 | 1.2 | 1 | 3.084 | Sq. Mt |  |  |  | 0.45
8 | 4 | PW | 1 | 2.96 | 1.2 | 1 | 3.552 | Sq. Mt
9 | 5 | PW | 1 | 25.8 | 0.906 | 1 | 23.3748 | Sq. Mt
10 | 6 | PW | 2 | 8.5 | 0.9 | 1 | 15.3 | Sq. Mt
11 | 7 | PW | 1 | 5.8 | 0.56 | 1 | 3.248 | Sq. Mt
12 | 8 | PW | 2 | 1 | 0.3 | 1 | 0.6 | Sq. Mt
13 | 9 | PW | 2 | 3.2 | 0.3 | 1 | 1.92 | Sq. Mt
14 | 10 | PW | 1 | 2.75 | 0.6 | 1 | 1.65 | Sq. Mt
15 | 11 | PW | 1 | 2.2 | 0.3 | 1 | 0.66 | Sq. Mt
16 | 1 | PS | 1 | 0.9 | 3.8 | 1 | 3.42 | Sq. Mt
17 | 2 | PS | 1 | 5.4 | 0.35 | 1 | 1.89 | Sq. Mt
18 | STAIR-CASE |  | 1 | 2.3 | 1.8 | 1 | 4.14 | Sq. Mt | 0.45
19 | STAIR-CASE |  | 1 | 2.3 | 1.54 | 1 | 3.542 | Sq. Mt | 0.45
20 | STAIR-CASE |  | 1 | 2.3 | 1.28 | 1 | 2.944 | Sq. Mt
21 | STAIR-CASE |  | 1 | 2.3 | 1.02 | 1 | 2.346 | Sq. Mt |  |  |  | 3.42
22 | STAIR-CASE |  | 1 | 2.3 | 0.76 | 1 | 1.748 | Sq. Mt |  |  |  | 2.57
23 | STAIR-CASE |  | 1 | 2.3 | 0.46 | 1 | 1.058 | Sq. Mt |  |  |  | 0.45
24 | STAIR-CASE |  | 1 | 2.3 | 1.18 | 1 | 2.714 | Sq. Mt | 0.45
25 | STAIR-CASE |  | 1 | 2.3 | 0.9 | 1 | 2.07 | Sq. Mt | 0.45
26 | STAIR-CASE |  | 1 | 2.3 | 0.603 | 1 | 1.3869 | Sq. Mt
27 | STAIR-CASE |  | 1 | 2.3 | 0.307 | 1 | 0.7061 | Sq. Mt |  |  |  | 3.42
28 | STAIR-CASE |  | 1 | 2.3 | 1.06 | 1 | 2.438 | Sq. Mt |  |  |  | 2.57
29 | STAIR-CASE |  | 1 | 2.3 | 0.805 | 1 | 1.8515 | Sq. Mt |  |  |  | 0.45
30 | STAIR-CASE |  | 1 | 2.3 | 0.52 | 1 | 1.196 | Sq. Mt |  |  |  | 2.57
31 | STAIR-CASE |  | 1 | 2.3 | 0.26 | 1 | 0.598 | Sq. Mt |  |  |  | 0.45
[5 empty] | GRAND TOTAL |  | 256.6293 | Sq. Mt
[5 empty] | 256.6293 | 1700 | 436269.81 | IRS
Item No.9 20 mm thick sand faced cement plaster on wall upto 10 meters above ground level consisting of 12 mm thick backing coat of c.m. 1:3 (1 cement:3 sand) and 8 mm thick finishing coat of c.m.1:1 ( 1cement:1 white sand) etc. complete
Sr. No. | Description |  | No. | L | B | D | Qty | Unit
1 | Main Wall |  | 1 | 25.8 | 3.6 |  | 92.88 | CMt
1 | Main Wall |  | 2 | 3.2 | 0.46 |  | 2.944 | CMt
2 | Ceiling |  | 1 | 25.8 | 5.15 |  | 132.87 | CMt
3 | Beam Side |  | 16 | 5.15 | 0.565 |  | 46.556 | CMt
4 | Beam Side |  | 2 | 5.15 | 0.23 |  | 2.369 | CMt
5 | Front Beam |  | 2 | 25.8 | 0.565 |  | 29.154 | CMt
6 | Chhajja Ceiling |  | 1 | 25.8 | 1.23 |  | 31.734 | CMt
7 | CB Side |  | 18 | 1 | 0.565 |  | 10.17 | CMt
8 | Front Side |  | 1 | 25.8 | 0.565 |  | 14.577 | CMt | 8.5
9 | Front Chhajja |  | 1 | 25.8 | 1.23 |  | 31.734 | CMt | 1.25
10 | Side Chhajja |  | 2 | 11.45 | 1 |  | 22.9 | CMt | 0.45
11 | Side Chhajja (T) |  | 2 | 11.45 | 0.125 |  | 2.8625 | CMt | 1.23
11 | Side Chhajja (T) |  | 2 | 1 | 0.125 |  | 0.25 | CMt | 1.23
11 | Side Chhajja |  | 2 | 11.45 | 1 |  | 22.9 | CMt | 1.23
6 | Column |  | 7 | 6.28 | 0.225 | 3 | 29.673 | CMt
7 | PARAPET |  | 2 | 2.04 | 1.2 |  | 4.896 | CMt
8 | PARAPET |  | 1 | 2.04 | 0.23 |  | 0.4692 | CMt
9 | PARAPET |  | 2 | 3.42 | 1.2 |  | 8.208 | CMt |  |  |  | 2.96
10 | PARAPET |  | 1 | 3.42 | 0.23 |  | 0.7866 | CMt |  |  |  | 0.45
11 | PARAPET |  | 2 | 2.57 | 1.2 |  | 6.168 | CMt |  |  |  | 0.45
12 | PARAPET |  | 1 | 2.57 | 0.23 |  | 0.5911 | CMt |  |  |  | 0.675
13 | PARAPET |  | 2 | 2.96 | 1.2 |  | 7.104 | CMt |  |  |  | 0.675
14 | PARAPET |  | 1 | 2.96 | 0.23 |  | 0.6808 | CMt |  |  |  | 2.51
15 | PARAPET |  | 2 | 0.96 | 1.2 |  | 2.304 | CMt
16 | PARAPET |  | 1 | 0.96 | 0.23 |  | 0.2208 | CMt
17 | PARAPET |  | 4 | 8.5 | 0.95 |  | 32.3 | CMt
18 | PARAPET |  | 2 | 8.5 | 0.23 |  | 0 | CMt
19 | PARAPET |  | 2 | 25.8 | 0.95 |  | 49.02 | CMt
20 | PARAPET |  | 1 | 25.8 | 0.23 |  | 5.934 | CMt
21 | PARAPET |  | 1 | 25.8 | 1.23 |  | 31.734 | CMt
22 | MAIN WALL SIDE |  | 1 | 3.2 | 0.36 |  | 1.152 | CMt
23 | MAIN WALL SIDE |  | 1 | 3.15 | 0.36 |  | 1.134 | CMt
24 | Colum Offset |  | 13 | 0.12 | 1.8 |  | 2.808 | CMt
25 | Column Offset |  | 2 | 0.45 | 1.8 |  | 1.62 | CMt
26 | [6 empty] | 0 | CMt
27 | [6 empty] | 0 | CMt
[5 empty] | Grand Total |  | 630.704 | CMt
[5 empty] | 630.704 | 675 | 425725.2 | IRS
Providing and laying cement based water proofing of average 100mm thick in proper slope as per specifications:(a)cleaning rcc slab and and applying neat cement slurrymixed with water proofing compound.(b)providing and laying brickbat coba in CM1:4mixed with water proofing compoundand curing for period of 24 hours (c ) laying of 25 mm thick PCC 1:1.5:3 mix with 6mm &down size coarse aggregate and water proofing compound,finishing smooth,making half round vata at the junction of parapetwall&slab,and curing for 10 day
Sr. No. | Description |  | No. | L | B | D | Qty | Unit
1 | TERRACE |  | 1 | 25.8 | 8.5 | 1 | 219.3 | CMt
[5 empty] | GRAND TOTAL |  | 219.3 | Sq. Mt
[5 empty] | 219.3 | 1300 | 285090 | IRS
Providing & anchoring 16 mm tor bars as anchor bars with chemicals of standard company by drilling holes 150 mm deep, cleaning the hole etc.
1 | B-5 |  | 1 | 4 | 1 | 1 | 4 | Nos. |  |  |  | 3.42
2 | B-2 |  | 1 | 8 | 1 | 1 | 8 | Nos. |  |  |  | 2.57
3 | B-2 |  | 1 | 8 | 1 | 1 | 8 | Nos. |  |  |  | 0.45
4 | B-2 |  | 1 | 8 | 1 | 1 | 8 | Nos. |  |  |  | 2.57
5 | B-3 |  | 1 | 6 | 1 | 1 | 6 | Nos. |  |  |  | 0.45
[5 empty] | GRAND TOTAL |  | 34 | Nos.
[5 empty] | 34 | 2000 | 68000 | IRS

## BBD
BAR BENDING SCHEDULE
Structure ID | SUB ST. No. | Sub Structure | Detail of work | structure no | Diameter | Bar no. | Total Bar | Bar length | Total length | 8mm | 10mm | 12mm | 16mm | 20mm
FOOTING | F1 & F2 | JALI | S.Z | 2 | 10 | 15 | 30 | 1.83 | 54.9 | 0 | 54.9 | 0 | 0 | 0
|  |  | L.Z | 2 | 10 | 15 | 30 | 1.83 | 54.9 | 0 | 54.9 | 0 | 0 | 0
|  | Column | MAIN | 2 | 16 | 8 | 16 | 8 | 128 | 0 | 0 | 0 | 128 | 0
|  |  | STIRRUPS | 2 | 8 | 48 | 96 | 1.8 | 172.8 | 172.8 | 0 | 0 | 0 | 0
|  |  | STIRRUPS | 2 | 8 | 48 | 96 | 1.8 | 172.8 | 172.8 | 0 | 0 | 0 | 0
| F3 & F4 | JALI | S.Z | 2 | 10 | 13 | 26 | 1.52 | 39.52 | 0 | 39.52 | 0 | 0 | 0
|  |  | L.Z | 2 | 10 | 13 | 26 | 1.52 | 39.52 | 0 | 39.52 | 0 | 0 | 0
|  | Column | MAIN | 2 | 16 | 8 | 16 | 8 | 128 | 0 | 0 | 0 | 128 | 0
|  |  | STIRRUPS | 2 | 8 | 48 | 96 | 1.8 | 172.8 | 172.8 | 0 | 0 | 0 | 0
|  |  | STIRRUPS | 2 | 8 | 48 | 96 | 1.8 | 172.8 | 172.8 | 0 | 0 | 0 | 0
|  | BEAM | MAIN | 2 | 12 | 6 | 12 | 1.52 | 18.24 | 0 | 0 | 18.24 | 0 | 0
|  |  | STIRRUPS | 2 | 8 | 16 | 32 | 1.8 | 57.6 | 57.6 | 0 | 0 | 0 | 0
COLUMN | 1 TO 7 | Column | MAIN | 7 | 16 | 6 | 42 | 9 | 378 | 0 | 0 | 0 | 378 | 0
|  |  | STIRRUPS | 7 | 8 | 47 | 329 | 1.8 | 592.2 | 592.2 | 0 | 0 | 0 | 0
|  |  | OVERLAP | 7 | 16 | 6 | 42 | 0.65 | 27.3 | 0 | 0 | 0 | 27.3 | 0
| PARAPET | COLUMN | MAIN | 9 | 10 | 4 | 36 | 1.75 | 63 | 0 | 63 | 0 | 0 | 0
|  |  | STIRRUPS | 9 | 8 | 5 | 45 | 0.8 | 36 | 36 | 0 | 0 | 0 | 0
BEAM | CB1 HORIZONTAL | BEAM | TOP BAR | 2 | 16 | 4 | 8 | 1.5 | 12 | 0 | 0 | 0 | 12 | 0
|  |  | BOTTOM | 2 | 16 | 2 | 4 | 1.5 | 6 | 0 | 0 | 0 | 6 | 0
|  |  | OVERLAP | 2 | 16 | 4 | 8 | 0.5 | 4 | 0 | 0 | 0 | 4 | 0
|  |  | OVERLAP | 2 | 16 | 2 | 4 | 0.5 | 2 | 0 | 0 | 0 | 2 | 0
|  |  | STIRRUPS | 2 | 8 | 13 | 26 | 1.8 | 46.8 | 46.8 | 0 | 0 | 0 | 0
| B6 | BEAM | TOP BAR | 1 | 12 | 2 | 2 | 26.5 | 53 | 0 | 0 | 53 | 0 | 0
|  |  | BOTTOM | 1 | 12 | 3 | 3 | 26.5 | 79.5 | 0 | 0 | 79.5 | 0 | 0 | 329.3 | 0.39 | 128.427
|  |  | STIRRUPS | 1 | 8 | 258 | 258 | 1.85 | 477.3 | 477.3 | 0 | 0 | 0 | 0 | 136.5 | 0.89 | 121.485
|  |  | OVERLAP | 1 | 12 | 2 | 2 | 0.4 | 0.8 | 0 | 0 | 0.8 | 0 | 0
|  |  | OVERLAP | 1 | 12 | 3 | 3 | 0.4 | 1.2 | 0 | 0 | 1.2 | 0 | 0
|  |  | OVERLAP | 1 | 12 | 2 | 2 | 0.4 | 0.8 | 0 | 0 | 0.8 | 0 | 0
|  |  | OVERLAP | 1 | 12 | 3 | 3 | 0.4 | 1.2 | 0 | 0 | 1.2 | 0 | 0
|  |  | OVERLAP | 1 | 12 | 2 | 2 | 0.4 | 0.8 | 0 | 0 | 0.8 | 0 | 0
|  |  | OVERLAP | 1 | 12 | 3 | 3 | 0.4 | 1.2 | 0 | 0 | 1.2 | 0 | 0
| CB1 VERTICAL | BEAM | TOP BAR | 9 | 16 | 4 | 36 | 2.3 | 82.8 | 0 | 0 | 0 | 82.8 | 0
|  |  | BOTTOM | 9 | 16 | 2 | 18 | 2.3 | 41.4 | 0 | 0 | 0 | 41.4 | 0
|  |  | STIRRUPS | 9 | 8 | 16 | 144 | 1.8 | 259.2 | 259.2 | 0 | 0 | 0 | 0
|  |  | OVERLAP | 9 | 16 | 4 | 36 | 0.5 | 18 | 0 | 0 | 0 | 18 | 0
|  |  | OVERLAP | 9 | 16 | 2 | 18 | 0.5 | 9 | 0 | 0 | 0 | 9 | 0
| B5 | BEAM | TOP BAR | 1 | 12 | 2 | 2 | 4 | 8 | 0 | 0 | 8 | 0 | 0
|  |  | BOTTOM | 1 | 20 | 2 | 2 | 4 | 8 | 0 | 0 | 0 | 0 | 8
|  |  | L | 1 | 12 | 2 | 2 | 0.315 | 0.63 | 0 | 0 | 0.63 | 0 | 0
|  |  | L | 1 | 20 | 2 | 2 | 0.315 | 0.63 | 0 | 0 | 0 | 0 | 0.63
|  |  | OVERLAP | 1 | 12 | 2 | 2 | 0.36 | 0.72 | 0 | 0 | 0.72 | 0 | 0
|  |  | OVERLAP | 1 | 20 | 2 | 2 | 0.36 | 0.72 | 0 | 0 | 0 | 0 | 0.72
|  |  | STIRRUPS | 1 | 8 | 27 | 27 | 1.9 | 51.3 | 51.3 | 0 | 0 | 0 | 0
| B4 | BEAM | TOP BAR | 1 | 12 | 2 | 2 | 7.8 | 15.6 | 0 | 0 | 15.6 | 0 | 0
|  |  | BOTTOM | 1 | 20 | 3 | 3 | 7.8 | 23.4 | 0 | 0 | 0 | 0 | 23.4
|  |  | OVERLAP | 2 | 12 | 2 | 4 | 0.36 | 1.44 | 0 | 0 | 1.44 | 0 | 0
|  |  | OVERLAP | 2 | 20 | 2 | 4 | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 2.4
|  |  | CURTAILS | 1 | 20 | 2 | 2 | 2 | 4 | 0 | 0 | 0 | 0 | 4
|  |  | STIRRUPS | 1 | 8 | 52 | 52 | 1.9 | 98.8 | 98.8 | 0 | 0 | 0 | 0
| B5 | BEAM | TOP BAR | 2 | 12 | 2 | 4 | 3.45 | 13.8 | 0 | 0 | 13.8 | 0 | 0
|  |  | BOTTOM | 2 | 20 | 2 | 4 | 3.45 | 13.8 | 0 | 0 | 0 | 0 | 13.8
|  |  | OVERLAP | 2 | 12 | 2 | 4 | 0.36 | 1.44 | 0 | 0 | 1.44 | 0 | 0
|  |  | OVERLAP | 2 | 20 | 2 | 4 | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 2.4
|  |  | STIRRUPS | 2 | 8 | 23 | 46 | 1.9 | 87.4 | 87.4 | 0 | 0 | 0 | 0
| B4 | BEAM | TOP BAR | 1 | 12 | 2 | 2 | 7.45 | 14.9 | 0 | 0 | 14.9 | 0 | 0
|  |  | BOTTOM | 1 | 20 | 3 | 3 | 7.46 | 22.38 | 0 | 0 | 0 | 0 | 22.38
|  |  | OVERLAP | 1 | 12 | 2 | 2 | 0.36 | 0.72 | 0 | 0 | 0.72 | 0 | 0 | 6.86
|  |  | OVERLAP | 1 | 20 | 2 | 2 | 0.6 | 1.2 | 0 | 0 | 0 | 0 | 1.2 | 0.3
|  |  | CURTAILS | 1 | 20 | 2 | 2 | 5 | 10 | 0 | 0 | 0 | 0 | 10 | 0.3
|  |  | EXTRA | 1 | 16 | 2 | 2 | 2.6 | 5.2 | 0 | 0 | 0 | 5.2 | 0
|  |  | STIRRUPS | 1 | 8 | 52 | 52 | 1.9 | 98.8 | 98.8 | 0 | 0 | 0 | 0
| B5 | BEAM | TOP BAR | 1 | 12 | 2 | 2 | 4 | 8 | 0 | 0 | 8 | 0 | 0
|  |  | BOTTOM | 1 | 20 | 2 | 2 | 4 | 8 | 0 | 0 | 0 | 0 | 8
|  |  | L | 1 | 12 | 2 | 2 | 0.315 | 0.63 | 0 | 0 | 0.63 | 0 | 0
|  |  | L | 1 | 20 | 2 | 2 | 0.315 | 0.63 | 0 | 0 | 0 | 0 | 0.63
|  |  | OVERLAP | 1 | 12 | 2 | 2 | 0.36 | 0.72 | 0 | 0 | 0.72 | 0 | 0
|  |  | OVERLAP | 1 | 20 | 2 | 2 | 0.36 | 0.72 | 0 | 0 | 0 | 0 | 0.72
|  |  | STIRRUPS | 1 | 8 | 27 | 27 | 1.9 | 51.3 | 51.3 | 0 | 0 | 0 | 0
| B5 | BEAM | TOP BAR | 1 | 12 | 2 | 2 | 16.65 | 33.3 | 0 | 0 | 33.3 | 0 | 0
|  |  | BOTTOM | 1 | 20 | 2 | 2 | 16.65 | 33.3 | 0 | 0 | 0 | 0 | 33.3
|  |  | L | 1 | 12 | 2 | 2 | 0.315 | 0.63 | 0 | 0 | 0.63 | 0 | 0
|  |  | L | 1 | 20 | 2 | 2 | 0.315 | 0.63 | 0 | 0 | 0 | 0 | 0.63
|  |  | OVERLAP | 2 | 12 | 2 | 4 | 0.36 | 1.44 | 0 | 0 | 1.44 | 0 | 0
|  |  | OVERLAP | 2 | 20 | 2 | 4 | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 2.4
|  |  | STIRRUPS | 1 | 8 | 167 | 167 | 1.9 | 317.3 | 317.3 | 0 | 0 | 0 | 0
| B4 | BEAM | TOP BAR | 1 | 12 | 2 | 2 | 7.8 | 15.6 | 0 | 0 | 15.6 | 0 | 0
|  |  | BOTTOM | 1 | 20 | 3 | 3 | 7.8 | 23.4 | 0 | 0 | 0 | 0 | 23.4
|  |  | OVERLAP | 2 | 12 | 2 | 4 | 0.36 | 1.44 | 0 | 0 | 1.44 | 0 | 0
|  |  | OVERLAP | 2 | 20 | 2 | 4 | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 2.4
|  |  | CURTAILS | 1 | 20 | 2 | 2 | 2 | 4 | 0 | 0 | 0 | 0 | 4
|  |  | STIRRUPS | 1 | 8 | 52 | 52 | 1.9 | 98.8 | 98.8 | 0 | 0 | 0 | 0
|  |  | EXTRA | 1 | 16 | 4 | 4 | 2.6 | 10.4 | 0 | 0 | 0 | 10.4 | 0
| B5 | BEAM | TOP BAR | 1 | 12 | 2 | 2 | 4 | 8 | 0 | 0 | 8 | 0 | 0
|  |  | BOTTOM | 1 | 20 | 2 | 2 | 4 | 8 | 0 | 0 | 0 | 0 | 8
|  |  | L | 1 | 12 | 2 | 2 | 0.315 | 0.63 | 0 | 0 | 0.63 | 0 | 0
|  |  | L | 1 | 20 | 2 | 2 | 0.315 | 0.63 | 0 | 0 | 0 | 0 | 0.63
|  |  | OVERLAP | 1 | 12 | 2 | 2 | 0.36 | 0.72 | 0 | 0 | 0.72 | 0 | 0
|  |  | OVERLAP | 1 | 20 | 2 | 2 | 0.36 | 0.72 | 0 | 0 | 0 | 0 | 0.72
|  |  | STIRRUPS | 1 | 8 | 27 | 27 | 1.9 | 51.3 | 51.3 | 0 | 0 | 0 | 0
| B5 | BEAM | TOP BAR | 1 | 12 | 2 | 2 | 13 | 26 | 0 | 0 | 26 | 0 | 0
|  |  | BOTTOM | 1 | 20 | 2 | 2 | 13 | 26 | 0 | 0 | 0 | 0 | 26
|  |  | L | 1 | 12 | 2 | 2 | 0.315 | 0.63 | 0 | 0 | 0.63 | 0 | 0
|  |  | L | 1 | 20 | 2 | 2 | 0.315 | 0.63 | 0 | 0 | 0 | 0 | 0.63
|  |  | OVERLAP | 1 | 12 | 2 | 2 | 0.36 | 0.72 | 0 | 0 | 0.72 | 0 | 0
|  |  | OVERLAP | 1 | 20 | 2 | 2 | 0.6 | 1.2 | 0 | 0 | 0 | 0 | 1.2
|  |  | STIRRUPS | 1 | 8 | 87 | 87 | 1.9 | 165.3 | 165.3 | 0 | 0 | 0 | 0
| B3 VERTICAL | BEAM | TOP BAR | 2 | 16 | 2 | 4 | 9.9 | 39.6 | 0 | 0 | 0 | 39.6 | 0
|  |  | BOTTOM | 2 | 20 | 4 | 8 | 9.9 | 79.2 | 0 | 0 | 0 | 0 | 79.2
|  |  | CURTAILS | 2 | 20 | 3 | 6 | 6.96 | 41.76 | 0 | 0 | 0 | 0 | 41.76
|  |  | STIRRUPS | 2 | 10 | 98 | 196 | 1.9 | 372.4 | 0 | 372.4 | 0 | 0 | 0
|  |  | L | 4 | 12 | 2 | 8 | 0.315 | 2.52 | 0 | 0 | 2.52 | 0 | 0
|  |  | L | 4 | 20 | 4 | 16 | 0.315 | 5.04 | 0 | 0 | 0 | 0 | 5.04
| B2 VERTICAL | BEAM | TOP BAR | 6 | 20 | 3 | 18 | 9.9 | 178.2 | 0 | 0 | 0 | 0 | 178.2
|  |  | BOTTOM | 6 | 20 | 5 | 30 | 9.9 | 297 | 0 | 0 | 0 | 0 | 297
|  |  | CURTAILS | 6 | 20 | 3 | 18 | 6.22 | 111.96 | 0 | 0 | 0 | 0 | 111.96
|  |  | STIRRUPS | 6 | 10 | 98 | 588 | 1.9 | 1117.2 | 0 | 1117.2 | 0 | 0 | 0
|  |  | L | 12 | 20 | 2 | 24 | 0.315 | 7.56 | 0 | 0 | 0 | 0 | 7.56
|  |  | L | 12 | 20 | 4 | 48 | 0.315 | 15.12 | 0 | 0 | 0 | 0 | 15.12
| B1 VERTICAL | BEAM | TOP BAR | 1 | 10 | 3 | 3 | 7.3 | 21.9 | 0 | 21.9 | 0 | 0 | 0
|  |  | BOTTOM | 1 | 20 | 3 | 3 | 7.3 | 21.9 | 0 | 0 | 0 | 0 | 21.9
|  |  | CURTAILS | 1 | 20 | 2 | 2 | 4.3 | 8.6 | 0 | 0 | 0 | 0 | 8.6
|  |  | STIRRUPS | 1 | 8 | 65 | 65 | 1.5 | 97.5 | 97.5 | 0 | 0 | 0 | 0
|  |  | OVERLAP | 1 | 20 | 2 | 2 | 0.6 | 1.2 | 0 | 0 | 0 | 0 | 1.2
|  |  | OVERLAP | 1 | 20 | 4 | 4 | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 2.4
CHIPIA | FRONT CHHAJJA | CHHAJJA | CHIPIA | 1 | 10 | 222 | 222 | 2.9 | 643.8 | 0 | 643.8 | 0 | 0 | 0
|  |  | CHIPIA | 2 | 10 | 75 | 150 | 2.9 | 435 | 0 | 435 | 0 | 0 | 0
SLAB | SLAB S1 | S1-1 | MAIN | 1 | 12 | 44 | 44 | 4.2 | 184.8 | 0 | 0 | 184.8 | 0 | 0 | 8710
|  |  | DIST. | 1 | 10 | 27 | 27 | 10 | 270 | 0 | 270 | 0 | 0 | 0 | 125
|  |  | EXTRA |  | 12 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 69.68
|  | S1-2 & 3 | MAIN | 1 | 12 | 88 | 88 | 8.4 | 739.2 | 0 | 0 | 739.2 | 0 | 0
|  |  | DIST. | 1 | 10 | 54 | 54 | 10 | 540 | 0 | 540 | 0 | 0 | 0
|  |  | EXTRA |  | 12 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 6.89
|  | S1-4 | MAIN | 1 | 12 | 71 | 71 | 3 | 213 | 0 | 0 | 213 | 0 | 0
|  |  | DIST. | 1 | 10 | 13 | 13 | 10 | 130 | 0 | 130 | 0 | 0 | 0
|  |  | EXTRA |  | 12 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | S1-5 | MAIN | 1 | 12 | 71 | 71 | 3 | 213 | 0 | 0 | 213 | 0 | 0 |  |  | 0.45
|  |  | DIST. | 1 | 10 | 13 | 13 | 10 | 130 | 0 | 130 | 0 | 0 | 0 | 2.51
|  |  | EXTRA |  | 12 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.3
|  | S1-6 & 7 | MAIN | 1 | 12 | 88 | 88 | 8.4 | 739.2 | 0 | 0 | 739.2 | 0 | 0
|  |  | DIST. | 1 | 10 | 43 | 43 | 7 | 301 | 0 | 301 | 0 | 0 | 0
|  |  | EXTRA |  | 12 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | S1-8 | MAIN | 1 | 12 | 44 | 44 | 4.2 | 184.8 | 0 | 0 | 184.8 | 0 | 0
|  |  | DIST. | 1 | 10 | 27 | 27 | 10 | 270 | 0 | 270 | 0 | 0 | 0
|  |  | EXTRA |  | 12 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7340 |  | 6.89
| SLAB S2 | S2-1 | MAIN | 1 | 8 | 7 | 7 | 4.2 | 29.4 | 29.4 | 0 | 0 | 0 | 0
|  |  | DIST. | 1 | 8 | 27 | 27 | 1.3 | 35.1 | 35.1 | 0 | 0 | 0 | 0
|  | S2-2 | MAIN | 1 | 8 | 7 | 7 | 4.2 | 29.4 | 29.4 | 0 | 0 | 0 | 0
|  |  | DIST. | 1 | 8 | 27 | 27 | 1.3 | 35.1 | 35.1 | 0 | 0 | 0 | 0
|  | S2-3 | MAIN | 1 | 8 | 7 | 7 | 4.2 | 29.4 | 29.4 | 0 | 0 | 0 | 0
|  |  | DIST. | 1 | 8 | 27 | 27 | 1.3 | 35.1 | 35.1 | 0 | 0 | 0 | 0
|  | S2-4 | MAIN | 1 | 8 | 7 | 7 | 3 | 21 | 21 | 0 | 0 | 0 | 0 |  |  | 0.45
|  |  | DIST. | 1 | 8 | 13 | 13 | 1.3 | 16.9 | 16.9 | 0 | 0 | 0 | 0 | 2.51
|  | S2-5 | MAIN | 1 | 8 | 7 | 7 | 3 | 21 | 21 | 0 | 0 | 0 | 0
|  |  | DIST. | 1 | 8 | 13 | 13 | 1.3 | 16.9 | 16.9 | 0 | 0 | 0 | 0
|  | S2-6 | MAIN | 1 | 8 | 7 | 7 | 4.4 | 30.8 | 30.8 | 0 | 0 | 0 | 0
|  |  | DIST. | 1 | 8 | 21 | 21 | 1.3 | 27.3 | 27.3 | 0 | 0 | 0 | 0
|  | S2-7 | MAIN | 1 | 8 | 7 | 7 | 4.4 | 30.8 | 30.8 | 0 | 0 | 0 | 0
|  |  | DIST. | 1 | 8 | 22 | 22 | 1.3 | 28.6 | 28.6 | 0 | 0 | 0 | 0
|  | S2-8 | MAIN | 1 | 8 | 7 | 7 | 4.2 | 29.4 | 29.4 | 0 | 0 | 0 | 0 |  |  | 0.45
|  |  | DIST. | 1 | 8 | 27 | 27 | 1.3 | 35.1 | 35.1 | 0 | 0 | 0 | 0 | 2.51
PLINTH SLAB | PLINTH | PS-1 | HORIZONTAL | 1 | 8 | 27 | 27 | 26 | 702 | 702 | 0 | 0 | 0 | 0 | 0.3
|  |  | VERTICAL | 1 | 8 | 112 | 112 | 7.8 | 873.6 | 873.6 | 0 | 0 | 0 | 0 | 0.41
Coping | Below Main Wall | Expansion Joint-1 | TOP BAR | 1 | 10 | 30 | 30 | 1 | 30 | 0 | 30 | 0 | 0 | 0
|  |  | BOTTOM | 1 | 10 | 5 | 5 | 7 | 35 | 0 | 35 | 0 | 0 | 0
|  | Expansion Joint-2 (a) | CURTAILS | 1 | 10 | 4 | 4 | 2.2 | 8.8 | 0 | 8.8 | 0 | 0 | 0
|  |  | STIRRUPS | 1 | 10 | 10 | 10 | 0.75 | 7.5 | 0 | 7.5 | 0 | 0 | 0
|  | Expansion Joint-3 (b) | Main Bar | 1 | 10 | 6 | 6 | 3.6 | 21.6 | 0 | 21.6 | 0 | 0 | 0
|  |  | STIRRUPS | 1 | 10 | 16 | 16 | 1.6 | 25.6 | 0 | 25.6 | 0 | 0 | 0
|  | Expansion Joint-4 | Main Bar | 1 | 10 | 6 | 6 | 6.8 | 40.8 | 0 | 40.8 | 0 | 0 | 0
|  |  | STIRRUPS | 1 | 10 | 30 | 30 | 1.6 | 48 | 0 | 48 | 0 | 0 | 0
|  |  | Extra at End | 1 | 10 | 10 | 10 | 1.08 | 10.8 | 0 | 10.8 | 0 | 0 | 0
[6 empty] | Total Length |  |  |  | 5305 | 4711.24 | 2588.97 | 891.7 | 971.53
[6 empty] | Unit Weight of Diameter |  |  |  | 0.39 | 0.62 | 0.89 | 1.58 | 2.47
[6 empty] | Total Weight |  |  |  | 2068.95 | 2920.9688 | 2304.1833 | 1408.886 | 2399.6791
[6 empty] | GRAND TOTAL |  |  |  | 11102.6672 | Kgs